K i l d a r e

County Council

Comhairle Contae

C h i l l  D a r a

Annual Report 2011

Internal Audit

and

Checking Section

Table of Contents

1.	Introduction	3

2.	Audit approach	3

3.    Status of 2011 Audit Plan	4

3.1   Completed Audits………………………………………………...	…..4

3.2   Audits commenced prior to year end……………………………….	4

3.3   Audits not commenced, carried forward to 2012………………….	4

4.   Miscellaneous Work	5

5.  Checking Report 2011	5

6.  Audit Committee	6

7.  Staffing	6

8.  Training, Staff Development and Conferences	6

9.  Conclusion	6

Appendix 1       Audit Procedure Update	6

Appendix 2       Internal Audit Plan 2011 Status at 31/12/2011	8

# Internal Audit Annual Report 2011

###### 1.	Introduction

The Audit Plan for 2011 was prepared following discussion with and input from the Audit Committee. Each Director of Service and Head of Function were consulted and the plan was approved by the Manager and Management Team at a meeting of 22/02/2011.

The Audit Plan contained 16 audits spread across the Directorates.

Some of the Audits involved staff from outside of HQ and as such on site visits and interviews were necessary. These included the audit on Branch Libraries and the Litter Control Audit. The Risk Management Process audit involved staff from all sections and considerable coordination was required.

###### Audit approach

The Audit approach in 2011 continued to develop from the procedures introduced in 2010 (*see new 2011 procedures). Recommendations made by Internal Audit were followed up with the relevant sections for confirmation of implementation and a report brought to the Audit Committee. The Audit Committee requested that where recommendations are not accepted by a section that this be explained and reported on to the committee and this process commenced towards the end of 2011. The committee also suggested the numbering of individual audit recommendations to assist in tracking and this has been completed in addition to numbering each audit report within each calendar year.

Emphasis continues to be placed on communication during audits and on the fact that Internal Audit should be viewed as adding value to sections through their advice and consultation role.

It was agreed during the year that the senior executive officer would be the main contact point within each section to facilitate an improvement in the flow of information between Internal Audit and the individual sections at audit stage and also at review of audit recommendation stage.

The main audit work is carried out by the two staff officers and one assistant staff officer with administrative support from the clerical officer who also carries out some checking duties. The Head of Internal Audit is involved at the initial stage, meeting with auditees and planning the audit and then takes the role of reviewing the audit findings and helping shape the report and recommendations.

The Audit Plan for 2012 will be drafted in line with the number of audit days available to Internal Audit Section.

###### 3.  Status of 2011 Audit Plan

Some of the scheduled Audits were cancelled for reasons outlined below. The audit on Dev. Levies scheduled for Quarter 4 was cancelled as the Local Government auditor had commenced a survey on progress on previous recommendations. The audit on verification of EU expenditure, Quarter 4, was cancelled following confirmation from the ERDF Audit Authority that funding was now closed and no audits were necessary.

Housing Section requested and were granted approval by the Manager to have the audit on the ERG/DPG grants scheduled for Quarter 2, deferred.

The end of year report on the 2011 plan is attached as an appendix.

There were some considerable time delays in producing draft and final reports due to poor responses from departments and Internal Audit would hope to see improvements in 2012.

### 3.1   Completed Audits

  - Stock take of Newbridge Stores (Annual) 2010

  - Risk Management Process

  - Unauthorised Development Procedure

  - Stock Management and Control / Vacant Houses

  - Bonds – Unfinished developments

  - Motor Tax Office

  - Administration of Fire service

  - Branch Libraries – Cost Management comparisons

  - Receipt and Lodgement checking (ongoing)

### 3.2   Audits commenced prior to year end

- Litter Control (street cleaning and Litter Warden service)

- Spot checks on Capital Projects

- Review of Parking procedures in Athy Town Council (requested late 2011)

### 3.3   Audits not commenced, considered for  2012

- Voluntary Housing

- Service Indicators

###### 4.   Miscellaneous Work

The 2010 Newbridge store stocktake report contained a recommendation that all future stocktakes would be carried out by Stores staff with Internal Audit carrying out spot checks for accuracy. As a result, Internal Audit were involved in meetings and consultation throughout the year for the handover of this responsibility. A similar but less time consuming process occurred with the Motor Tax Office who now also carry out their own stock take.

The review of audit recommendations involves considerable communications and follow up with the various sections.

An investigation into a suspected case of fraud was commenced before year end.

###### 5.  Checking Report 2011

Checking is traditionally carried out in all areas where cash is handled by employees within the council. Areas checked in 2011 include

- Revenue Collectors

- Motor Tax office

- Cash offices in HQ, Naas and Athy

- Libraries HQ

- Kilmeade Burial ground caretakers

- Newbridge Halting site

- Civic Amenity Centres Athy/Silliot Hill

- Pay parking permits

- Dog Warden

The primary function of checking is to reconcile monies received with lodgements made by the recipient to the bank.

In 2010 significant changes occurred as responsibility was returned to supervisors at some traditional checking locations i.e. burial grounds and revenue collectors. In 2011 the cash offices in HQ, Athy Town Council and Naas Town Council and the Planning cash office were notified that responsibility for ensuring the controls were in place and operating successfully rested with the local supervisors but that Internal Audit would carry out spot checks or carry out  complete audits in the future. The areas of Pay Parking and Motor Tax were advised similarly that local supervisors are responsible for controls within the sections. This removes Internal Audit from being part of the operation process in keeping with the need for independence as outlined in the Internal Audit Charter.

###### 6.  Audit Committee

Reports were presented to the Audit committee at each of their five meetings in 2011 and the committee’s contribution and support for the Internal Audit function is hereby acknowledged.

###### 7.  Staffing

As at 31/12/2011 the full staff complement of 5 consists of one grade 7, two grade 5s (one 4 days per week, one week on week off), one grade 4 and one grade 3.

###### 8.  Training, Staff Development and Conferences

The Head of Internal Audit commenced a Professional Certificate in Corporate Governance through the IPA which will conclude in April 2012.

The Head of Internal Audit also attended a Legal course ran by the IPA through 2011 which focussed on each section within Local Authorities their main functions and the legislation on which these functions are based. General information on the Law, the courts etc. was also covered. These sessions were held in house and will continue into 2012.

Other courses/seminars attended by staff include, Dignity in the Workplace, Internal Audit processes – good practice and benchmarking (IIA) and the IIA Ireland Annual Conference.

The Local Authority Internal Audit Development Group (LAIADG) continues to meet biannually and is a valuable source of information and experience sharing. As well as meetings, information is shared through the year as Internal Audit in each local authority commences new audits and seeks advice from the other group members.

###### 9.  Conclusion

I wish to express my appreciation of the courtesy and consideration shown to the Internal Audit staff while conducting audits and carrying out checking.

Eamon Fagan

Head of Internal Audit

2011

###### Appendix 1

Audit Procedure update

The following sets out the new procedure which will be followed by Internal Audit in the course of each audit. The Audits for each year are outlined in the Audit Plan which also indicates the intended quarter within which each will commence and the anticipated no. of Audit days available overall and allocated for each audit. Additional audits may also be carried out when sufficient concerns or Risks are highlighted.

- Advise Director /Head of Function of intention to commence audit and seek meeting to discuss Audit Approach and  Management concerns.

- Meet with local management to obtain understanding of system to be audited and details of staff working in the area. Obtain procedures manual, Risk register and any other relevant documentation.

- Advise Auditee of proposed timeframe for issuing of draft and Final reports.

- Internal Audit prepare a) Audit Planning Memorandum b) Control Evaluation form and c) Audit programme. These documents set out the audit preparation and work programmes including the Sample population and Tests to be carried out. They form part of the audit file and serve as back up to the Audit report and findings.

- Audit is conducted and findings outlined and Ranked

- Internal Audit holds an Exit meeting with the Senior executive officer (or equivalent). The purpose of this is to advise of the findings (this will also take place throughout the audit itself) and ensure that no inaccuracies or misunderstanding of facts exist. The Rank assigned to the finding should also be considered at this meeting plus the implementation date if Recommendation agreed.

- A draft report will then issue to the Senior Executive Officer (or equivalent) inviting a written response within one week.

- The Final report will then issue containing the Managements response (for both Agreed and not Agreed actions). This report will be circulated to the Management team and the Executive summary will be forwarded to the Audit Committee.

- The Agreed actions/Recommendations will be numbered to facilitate tracking and will be presented to the Audit Committee. Prior to each Audit committee meeting an update will be sought via the Senior Executive Officer.

- Spot checks will also be carried out to verify Implementation of Agreed actions.

- Recommendations not Agreed by management will be presented to the Audit Committee detailing management’s response.

Eamon Fagan

Head of Internal Audit

31/12/2011

###### Appendix 2

Internal Audit Plan 2011 Status at 31/12/2011

| No | Audit | Commencement Quarter | Status |
| --- | --- | --- | --- |
|  | Stocktake of Newbridge Stores (Annual) 2010 | Q 1 | Final issued 16/03/11 |
|  | Risk management process | Q 1 | Final issued 22/07/11 |
|  | Unauthorised development procedure | Q 1 | Final issued 01/07/11 |
|  | Stock management and control /vacant houses | Q 1 | Final issued 21/10/11 |
|  | Grant Schemes – DPG/ERG | Q 2 | Scheduled to commence w/b 16/05/11 Deferred on request of Hsg Mgt and agreed by Manager. C/F to 2012 |
|  | Bonds – Unfinished Developments | Q 2 | Final issued 21/10/11 |
|  | Motor Tax Office | Q 2 | Final issued 26/08/11 |
|  | Administration of Fire Service HQ | Q 2 | Final issued 10/10/11 |
|  | Litter Control (Street cleaning and litter warden service) | Q 3 | Commenced 12/09/2011 |
|  | Branch libraries – Cost management comparisons | Q 3 | Final issued 13/10/11 |
|  | Voluntary Housing | Q 3 | Not commenced. Reconsidered for inclusion in 2012 |
|  | Dev Levies – verifying compliance with VFM report 26 | Q 4 | Cancelled due to LG audit on progress |
|  | Service Indicators | Q 4 | C/F TO 2012 |
|  | 5% verification of EU funded expenditure | Q 4 | No longer necessary |
|  | Spot checks of Capital Projects funded by DOEHLG | Q 4 | Commenced 31/10/2011 |
| 16. | Receipt and lodgement checking | Q1,2,3,4 | Review of each checking area ongoing |