K i l d a r e

County Council

Comhairle Contae

C h i l l  D a r a

Annual Report 2014

Internal Audit

Table of Contents

1.	Introduction	3

2.	Audit approach	3

3.	Status of 2014 Audit Plan	3

3.1	Completed Audits	4

3.2	Audits at draft stage	4

3.3	Audits commenced prior to year end	4

3.4	Audits not commenced	4

4.	Miscellaneous Work	5

5.	Checking Report 2014	5

6.	Audit Committee	5

7.	Staffing	5

8.	Training, Staff Development and Conferences	6

9.	Conclusion	6

Appendix 1	7

Appendix 2	7

# Internal Audit Annual Report 2014

###### Introduction

The Audit Plan for 2014 was prepared following discussion with and input from the Audit Committee. Each Director of Service and Head of Function were consulted and the plan was approved by the Manager and Management Team at a meeting of 21/01/2014.

The Audit Plan contained 17 audits spread across the Directorates.

Some of the Audits involved staff from outside of HQ and as such on site visits and interviews were necessary. These included the audit on Athy Burial Ground and the Council Depot review.

###### Audit approach

The Audit approach in 2014 was based on procedures the latest version of which is attached. These procedures are continuously updated to reflect best practise and incorporating experience gained from each audit. Recommendations made by Internal Audit were followed up with the relevant sections for confirmation of implementation and a report brought to the Audit Committee. Spot checks were also carried out and evidence of Implementation of Actions was sought.

The main audit work is carried out by the two staff officers and one assistant staff officer with administrative support from the clerical officer who also carries out some checking duties. The Head of Internal Audit is involved at the initial stage, meeting with auditees and planning the audit and then takes the role of reviewing the audit findings and helping shape the report and recommendations.

The Audit Plan for 2015 will be drafted in line with the number of audit days available to Internal Audit Section.

###### Status of 2014 Audit Plan

The end of year report on the 2014 plan is attached as an appendix.

###### Completed Audits

| 14/1 | Litter Control (Street Cleaning and Litter Warden Service) |
| --- | --- |
| 14/2 | Parking Reconciliation Naas Town Council |
| 14/3 | Burial Ground Athy Town Council |
| 14/4 | Capital projects water services |
| 14/5 | Misc debtors sludge treatment/landfill |
| 14/6 | 2013 Stores stocktake |
| 14/7 | Housing Maintenance- Town Council Comparisons |

###### Audits at draft stage

  - Development contributions procedures- Draft issued 12/11/2014

###### Audits commenced prior to year end

- CORE –Payrol/HR processes (discussion doc issued December 2014)

- Loans Collection (discussion doc issued December 2014)

- VFM Part V Procedures (commenced oct 2014)

- Root and Branch review of Council depots(discussion doc issued 25/09/2014)

- Procedures at closed burial ground Athy (discussion doc issued in nov 2014)

###### Audits not commenced

- Community Grants –(Internal review commenced in june 2014)

- Fire safety Certs/Disability Access certs (not commenced and not considered priority in 2015)

- Control of Horses/Collection of Dog licenses( carried over to 2015 Plan)

- Community Grant funded organisations- Governance ( carried over to 2015)

###### Miscellaneous Work

Additional work carried out in 2014:

- One new investigation

- Follow up actions on previous suspected criminal action

- Review of Audit Recommendations

- Minor Cash discrepancies at cash receipting points.

Some of the investigative work involves communication with non kcc staff and the review of audit recommendations continues to involve considerable communications and follow up with the various sections.

5.   Checking Report 2014

The primary function of checking is to reconcile monies received with lodgements made by the recipient to the bank. Internal Audit had traditionally carried out checking in all areas where cash was handled by employees within the council however over the past few years has transferred these duties to local management. Internal Audit now spot check that checking procedures are being followed and also spot check individual areas. No issues of concern were identified in 2014 and a schedule of areas to be checked has been drawn up and assigned for 2015.

###### Audit Committee

Reports were presented to the Audit committee at each of their meetings in 2014 and the committee’s contribution and support for the Internal Audit function is hereby acknowledged.

###### Staffing

The full staff complement of 5 is listed below indicating grade and full time equivalent.

Administrative Officer  1.

Staff Officer                   .8

Staff Officer                   .5

Assistant Staff Officer    .8

Clerical Officer             1.

###### Training, Staff Development and Conferences

Two staff attended a seminar in the IPA on Internal Audit in the Irish Public sector. The Head of Internal Audit also attended a session on the new Audit Committee legislation facilitated by the IPA held in house.

The Local Authority Internal Audit Development Group (LAIADG) continues to meet biannually and is a valuable source of information and experience sharing. As well as meetings, information is shared through the year as Internal Audit in each local authority commences new audits and seeks advice from the other group members.

###### Conclusion

I wish to record my appreciation of the courtesy and consideration shown to the Internal Audit staff while conducting audits and carrying out checking.

Eamon Fagan

Head of Internal Audit

25/02/2015

###### Appendix 1

Audit Procedure update

The following sets out the procedure which will be followed by Internal Audit in the course of each audit. The audits for each year are outlined in the Audit Plan which also indicates the intended quarter within which each will commence. Additional audits will also be carried out when sufficient concerns or risks are highlighted.

- Advise Director /Head of Function of intention to commence audit and seek meeting to discuss audit approach and management concerns.

- Meet with local management to obtain understanding of system to be audited and details of staff working in the area. Obtain procedures manual, Risk Register and any other relevant documentation.

- Advise auditee of proposed timeframe for issuing of draft and final reports.

- Internal Audit prepare a) Audit Planning Memorandum b) Control Evaluation form and c) Audit programme. These documents set out the audit preparation and work programmes including the sample population and tests to be carried out. They form part of the audit file and serve as back up to the Audit report and findings.

- Audit is conducted and Findings, Implications and Recommendations are laid out in a discussion document. Delays of over one week to a request for information will be presented in a monthly report to the Chief Executive.

- Internal Audit holds an exit meeting with the Senior Executive Officer (or equivalent) to review the discussion document. The purpose of this is to discuss the findings (this will also take place throughout the audit itself) and ensure that no inaccuracies or misunderstanding of facts exist. The priority ranking assigned to the finding should also be considered at this meeting plus the implementation date if the recommendation is agreed. Delays of over one week to a meeting request will be presented in a monthly report to the Chief Executive.

- Findings and Recommendations which are not accepted by the relevant section will be reported on to the Chief Executive for ruling.

- A draft report will then issue to the Director  and Senior Executive Officer (or equivalent) inviting a written response within one week. Delays in responding to the Draft report within the agreed timeframe will be presented to the Chief Executive in a monthly report.

- The final report will then issue containing the Managements response (for both agreed and not agreed actions). This report will be circulated to the Management team and then on to the Audit Committee. The agreed actions/recommendations will be numbered to facilitate tracking.

- Prior to each Audit Committee meeting an update on progress with Implementation of Agreed Actions will be sought via the Senior Executive Officer and a report will be presented to the Committee. Delays in supplying information on the Implementation of Agreed Actions will be presented to the Chief Executive in a monthly report.

- Changes to Implementation dates of Agreed Action or to the Actions themselves will be presented to the Chief Executive in a monthly report.

- Spot checks will be carried out to verify implementation of agreed actions as reported.

- Eamon Fagan

Head of Internal Audit

08/12/2014

###### Appendix 2

Internal Audit Plan 2014

Progress December 2014

| No. | Audit | Quarter | Audit Days available | No. of Audit days allocated | Status |
| --- | --- | --- | --- | --- | --- |
|  | ENV/TRANSPORTATION Litter Warden and Street cleaning | Q1 | 611 | 1 | Final Report issued 31/01/2014 |
|  | Review and Spot check on Audit Recommendations | Q1,2,3,4 | 610 | 70 | Ongoing |
|  | Spot check on Annual Stock take in Newbridge Stores year 2013 | Q1 | 540 | 5 | Final Report 23/07/2014 |
| 4. | Capital Project WATER SERVICES – | Q1 | 535 | 10 | Final Report 09/06/2014 |
| 5. | ENVIRONMENT/WATER Misc Debtors - Sludge Treatment Plants - Landfill Levies, | Q1 | 525 | 10 | Final Report 18/06/2014 |
| 6. | CORE Payroll FINANCE- | Q1 | 515 | 20 | Discussion document issued Dec 2014 |
| 7. | HOUSING Hsg maintenance TC comparisons | Q1 | 495 | 60 | Final Report issued 04/09/2014 |
| 8. | ATHY TOWN COUNCIL Burial Ground- Review of administrative and on site procedures. | Q1 | 435 | 30 | Final Report issued 20/05/2014 |
| 9. | NAAS TC Reconciliation of parking meter collections | Q2 | 405 | 20 | Final Report issued 14/05/2014 |
| 10. | HOUSIING/COMMUNITY Community Grants incl TC’s and other. | Q2 | 385 | 30 | Community have commenced their own review june 2014 |
| 11. | PLANNING Development Contributions –Collection and /or procedures around accessing and spending | Q2 | 355 | 60 | Draft Report issued 12/11/2014 |
| 12. | FINANCE Loans collection | Q2 | 295 | 40 | Discussion document issued Dec 2014 |
| 13. | VFM Part V - Athy and Naas – Registers up to date | Q3 | 255 | 20 | Commenced Oct 2014 |
| 14. | TRANSPORTATION Root and Branch review of Council Depot | Q3 | 235 | 60 | Discussion document issued 25/09/2014 awaiting meeting. |
| 15. | PLANNING Fire safety certs/ Disability Access certs – Links with Planning Files | Q3 | 175 | 45 | Not commenced |
| 16. | ENVIRONMENT Control of horses /Collection of Dog Licences | Q4 | 130 | 50 | Not Commenced Carried over to 2015 |
| 17. | COMMUNITY Grant funded organisations | Q4 | 80 | 40 | Not Commenced Carried over to 2015 |